## Sheet1
insert "Agreement" or "Project Authorization" as the "Document" below
add additional "Modifications" as needed; copy-and-paste to retain layout and protect "sum-if" formulas for "Total Modifications"
pink cells indicate where project-specific-data must be entered
blue cells contain formulas which perform calculations on the entered data (DO NOT CHANGE these formulas)
the worksheet has example data filled-in the shaded cells, which can be deleted or overwritten
before saving, printing, and/or distributing:
change all text colors to black, and clear all highlights from the cells
adjust vertical page breaks and print area as needed
these yellow instruction lines are INTENTIONALLY OUTSIDE the print area; grid lines do not print
Professional Services Fees Back-Up Form
Firm: |  |  | name
address
city, state zip
UA Project Number: |  |  | 00-1234
UA Project Name: |  |  | Big Building Renovation
Firm's Invoice Number: |  |  | 2
Firm's Invoice Date: |  |  | 2000-02-18
Original Document
| Date: |  | 1999-09-01
Approved Modification(s) Description and Date:
| 1 | Add Room 123, Renderings, Model |  | 1999-11-15
| 2 | Add Graphic Design, Telecomm Design |  | 2000-01-05
3
Invoice Summary |  |  | Phase | Percent | Total | Previous | Current | Remaining
|  |  | Fee | Complete | Complete | Invoice(s) | Invoice | Balance
Original Amount
| Programming |  | 1000 | 100% | 1000 | 1000 | 0 | 0
| Conceptual Design |  | 0 | 0% | 0 | 0 | 0 | 0
| Schematic Design |  | 1000 | 100% | 1000 | 1000 | 0 | 0
| Design Development |  | 2000 | 100% | 2000 | 2000 | 0 | 0
| Construction Documents |  | 5000 | 50% | 2500 | 0 | 2500 | 2500
| Pricing |  | 1000 | 0% | 0 | 0 | 0 | 1000
| Construction Administration |  | 5000 | 0% | 0 | 0 | 0 | 5000
| Project Closeout |  | 1000 | 0% | 0 | 0 | 0 | 1000
| Warranty |  | 1000 | 0% | 0 | 0 | 0 | 1000
Total Original Amount |  |  | 17000 | 38.24% | 6500 | 4000 | 2500 | 10500
Modification 1
| Program |  | 100 | 100% | 100 | 100 | 0 | 0
| Conceptual Design |  | 0 | 0% | 0 | 0 | 0 | 0
| Schematic Design |  | 100 | 100% | 100 | 100 | 0 | 0
| Design Development |  | 200 | 100% | 200 | 100 | 100 | 0
| Construction Documents |  | 500 | 50% | 250 | 0 | 250 | 250
| Pricing |  | 0 | 0% | 0 | 0 | 0 | 0
| Construction Administration |  | 0 | 0% | 0 | 0 | 0 | 0
| Project Closeout |  | 0 | 0% | 0 | 0 | 0 | 0
| Warranty |  | 0 | 0% | 0 | 0 | 0 | 0
| Total Modification 1 |  | 900 | 72.22% | 650 | 300 | 350 | 250
Modification 2
| Program |  | 0 | 0% | 0 | 0 | 0 | 0
| Conceptual Design |  | 0 | 0% | 0 | 0 | 0 | 0
| Schematic Design |  | 0 | 0% | 0 | 0 | 0 | 0
| Design Development |  | 800 | 100% | 800 | 0 | 800 | 0
| Construction Documents |  | 1200 | 25% | 300 | 0 | 300 | 900
| Pricing |  | 0 | 0% | 0 | 0 | 0 | 0
| Construction Administration |  | 0 | 0% | 0 | 0 | 0 | 0
| Project Closeout |  | 0 | 0% | 0 | 0 | 0 | 0
| Warranty |  | 0 | 0% | 0 | 0 | 0 | 0
| Total Modification 2 |  | 2000 | 55% | 1100 | 0 | 1100 | 900
Modification 3
| Program |  | 0 | 0% | 0 | 0 | 0 | 0
| Conceptual Design |  | 0 | 0% | 0 | 0 | 0 | 0
| Schematic Design |  | 0 | 0% | 0 | 0 | 0 | 0
| Design Development |  | 0 | 0% | 0 | 0 | 0 | 0
| Construction Documents |  | 0 | 0% | 0 | 0 | 0 | 0
| Pricing |  | 0 | 0% | 0 | 0 | 0 | 0
| Construction Administration |  | 0 | 0% | 0 | 0 | 0 | 0
| Project Closeout |  | 0 | 0% | 0 | 0 | 0 | 0
| Warranty |  | 0 | 0% | 0 | 0 | 0 | 0
| Total Modification 3 |  | 0 | #DIV/0! | 0 | 0 | 0 | 0
Total All Modifications |  |  | 2900 | 60.34% | 1750 | 300 | 1450 | 1150
Total Fees |  |  | 19900 | 41.46% | 8250 | 4300 | 3950 | 11650